TAB WELLNESS COLLECTIVE

# Step 19 — Rebrand Transition & Launch Plan

TAB Massage & Fitness → TAB Wellness Collective

Transition objective Make the rebrand feel like an intentional evolution of the TAB clients already know — preserving trust, history, bookings, payments, referrals, search equity and client continuity while introducing the broader whole-person brand.

A new visitor should understand TAB Wellness Collective immediately, while an existing TAB Massage & Fitness client should experience the change as familiar, intentional and seamless.

# Executive Summary

Step 19 operationalizes the rebrand across every client-facing and internal touchpoint. The plan uses a phased migration so that the new brand can launch cleanly without sacrificing the digital and relationship equity accumulated under TAB Massage & Fitness.

## The five-phase transition model

| Phase | Purpose | Typical timing |
| --- | --- | --- |
| 0 — Clearance & Ownership | Complete naming/legal checks, secure domains/handles, inventory systems and confirm account control. | Before irreversible spend |
| 1 — Build Behind the Scenes | Prepare website, systems, forms, collateral, redirects and communications without public cutover. | T-8 to T-4 weeks |
| 2 — Pre-Launch Communication | Prepare clients, partners and team before they encounter the new identity. | T-3 to T-1 weeks |
| 3 — Launch / Cutover | Coordinate website, Google, Timely, Stripe, email, social, signage and internal changes. | Launch day |
| 4–5 — Transition to Steady State | Monitor, reduce confusion, preserve legacy pathways and gradually retire “formerly” language. | Launch to +6 months |

Governing principle Preserve legacy equity through redirects, aliases, continuity messaging and retained account history. Do not delete or recreate assets that can be migrated in place.

# 19.1 — Rebrand Transition Strategy

## The transition story

TAB Massage & Fitness is becoming TAB Wellness Collective.

The public explanation should stay simple: the name is evolving to better reflect the broader, whole-person approach TAB provides today — Massage & Bodywork, Personal Strength Training, Women’s Wellness Coaching and Holistic Life Coaching.

Same commitment. Broader expression of what TAB has become.

## Transition naming standard

Permanent brand: TAB Wellness Collective.

Philosophy: Transform. Align. Become.

Temporary transition phrase: “formerly TAB Massage & Fitness.”

Do not place “formerly…” inside the permanent logo or wordmark.

Use the transition phrase selectively for approximately 90–180 days where recognition matters.

# 19.2 — Detailed Transition Phases

## Phase 0 — Clearance & Ownership

Complete formal trademark clearance and Michigan entity/assumed-name work.

Secure the primary domain and relevant defensive domains.

Reserve preferred social handles.

Confirm administrative access to website/DNS, Google Business Profile, Search Console, Analytics, Timely, Stripe, email and social accounts.

Inventory all current brand touchpoints, vendor accounts, printed materials and recurring templates.

Preserve current website analytics, search performance, page inventory and backlink data.

Go / no-go gate Do not order permanent exterior signage or destroy legacy digital assets until naming clearance is resolved and critical account access is confirmed.

## Phase 1 — Build Behind the Scenes

Build and QA the new public website on the new domain.

Prepare My TAB architecture or a clear interim Client Login experience.

Configure new email aliases/addresses while preserving old ones.

Prepare Timely branding and booking-link changes.

Prepare Stripe customer-facing naming, receipts and portal branding.

Stage Google Business Profile assets and text.

Prepare social profile art, bios and launch posts.

Order signage and printed collateral.

Update forms, consent materials, client-facing PDFs and templates.

Build the old-to-new URL redirect map and SEO migration plan.

Prepare staff scripts and client/partner communications.

## Phase 2 — Pre-Launch Communication

Begin communicating approximately 2–3 weeks before launch. Existing clients should never encounter the new brand unexpectedly.

Explain what is changing: name, visual identity, website and expanded expression of services.

Explain why: the new brand better represents TAB’s whole-person approach.

Explain what is not changing: appointments, practitioners, client history, relationships and commitment to personalized care.

Clarify that clients should not need to take action unless specifically notified.

Introduce “Transform. Align. Become.” and the four service pillars.

## Phase 3 — Launch / Cutover

Make TAB Wellness Collective the public name across the website, signage and key digital profiles.

Publish the new website and enable permanent redirects from legacy URLs.

Update Timely business name, branding, location details, links and templates.

Update Stripe customer-facing branding, support details, receipt/invoice context and statement descriptor if required.

Update email signatures and activate the new-domain addresses/aliases.

Update Google Business Profile once the public website/signage supports the new real-world identity.

Update social display names, handles, artwork, bios and links.

Notify partners and publish the launch announcement.

Run end-to-end smoke testing on booking, forms, email and payment paths.

## Phase 4 — Transition Period

For roughly the first 90 days, use “TAB Wellness Collective — formerly TAB Massage & Fitness” where it materially reduces confusion. Monitor search, booking and client behavior closely.

## Phase 5 — Steady State

At roughly +3 to +6 months, TAB Wellness Collective should stand on its own. Legacy naming remains only where historically or operationally useful — redirects, old email aliases, the Our Story narrative and legal records.

# 19.3 — Website & Domain Migration

The domain migration is a major equity-preservation activity. The goal is to move to the new brand domain without throwing away the history and referral traffic attached to tabmassage.com.

## Domain strategy

Primary destination: tabwellnesscollective.com, subject to final availability/clearance.

Retain tabmassage.com indefinitely if renewal cost remains nominal.

Use server-side 301/308 permanent redirects from each meaningful old URL to its closest new equivalent.

Do not redirect every old page blindly to the homepage.

Retain legacy email-domain aliases in parallel with the website redirects.

| Legacy URL example | Recommended destination |
| --- | --- |
| tabmassage.com/ | tabwellnesscollective.com/ |
| /massage | /services/massage-bodywork |
| /personal-training | /services/personal-strength-training |
| /about | /about |
| Legacy article/resource | Matching new /resources article where available |

## Launch SEO checklist

Build and test the full redirect map before launch.

Avoid redirect chains and redirect loops.

Update internal links, canonical tags and XML sitemap.

Review robots.txt and remove any staging noindex directives.

Verify both domains in Google Search Console.

Submit the new sitemap and domain move/change-of-address workflow where applicable.

Update analytics/measurement configuration.

Crawl the legacy site and new site for 404s before and after launch.

Update major external backlinks and directory links where feasible.

Expect temporary search fluctuation while the new URLs are reprocessed.

# 19.4 — Google Business Profile & Local Search

The local listing should change only when the real-world identity is ready to support it. The website, visible branding and Business Profile should tell the same story.

## Recommended sequence

Install or make visible the new real-world/public branding.

Launch the website as TAB Wellness Collective.

Update the Google Business Profile and prepare for possible reverification.

## Profile updates

Business name

Primary and secondary categories where justified

Website URL

Appointment link

Business description

Services

Logo and cover imagery

Photos

Hours and contact details if needed

During the transition, “formerly TAB Massage & Fitness” can appear in explanatory copy but should not be inserted as part of the official business-name field unless it is genuinely part of the real-world name.

## NAP consistency

Maintain one canonical Name / Address / Phone / Website record and use it consistently across Google, Apple, Bing, Yelp, Facebook, local directories, professional listings and community partners.

# 19.5 — Timely Migration

Timely remains the appointment and scheduling system of record. The rebrand should update the existing Timely presence rather than forcing clients into a new scheduling history.

## Timely cutover checklist

Business name and logo

Business description

Website and social links

Location name

Client-facing contact information

Booking page branding

Email branding/templates

Invoice branding

Service names and descriptions

Service categories

Practitioner bios

Consultation/intake forms

Confirmation/reminder text

Cancellation copy

Notification continuity Already-sent reminders may still contain the legacy business name. Advance client communication reduces confusion during the overlap period.

# 19.6 — Stripe & Financial Experience

Stripe remains the payment and financial-transaction system of record. The transition should update customer-facing branding while preserving transaction history and avoiding any need to move card data into TAB systems.

Update public/business name where appropriate.

Update support email and support URL.

Refresh receipt, invoice and Customer Portal branding.

Review subscription and product names.

Review payment links and checkout descriptions.

Define and document the card-statement descriptor.

Keep card/bank information in Stripe rather than My TAB.

## Statement descriptor

Because the full public name may exceed processor descriptor limits, use a recognizable abbreviated financial descriptor such as TABWELLNESSCOLL rather than turning “TAB Wellness” into a secondary marketing brand.

# 19.7 — Email & Domain Migration

Create new-domain email addresses/aliases before launch.

Use role addresses such as hello@, support@ and billing@ where useful.

Preserve all legacy @tabmassage.com addresses as aliases/forwarders for years, potentially indefinitely.

Use a 90-day transitional signature that includes “formerly TAB Massage & Fitness.”

Avoid permanent auto-replies on legacy addresses; if used at launch, keep them short and temporary.

You’re in the right place — TAB Massage & Fitness is now TAB Wellness Collective. Your message has reached us normally.

# 19.8 — Social Media Transition

Keep existing accounts wherever possible. Rebranding in place preserves followers, engagement history, reviews and social proof.

Change display name and handle when available.

Update profile icon and cover/banner.

Update bio, website and booking links.

Pin a launch/rebrand announcement.

Use “formerly TAB Massage & Fitness” for approximately 60–90 days where helpful.

After transition, simplify the bio around whole-person wellness and Transform. Align. Become.

## Suggested launch-post structure

TAB is evolving. TAB Massage & Fitness is now TAB Wellness Collective.

Then explain that the new name reflects the broader whole-person model and explicitly list the four service pillars before reinforcing continuity.

# 19.9 — Physical Signage & Environment

## Exterior inventory

Building sign

Roadside sign

Door/window vinyl

Hours signage

Parking signage

Directional signs

## Interior inventory

Reception branding

Service-room signage

Training space graphics

Wall graphics

Service/pricing boards

Printed client information

Temporary transition sign TAB Massage & Fitness has become TAB Wellness Collective. You’re in the right place.

# 19.10 — Printed & Operational Materials

## Client-facing materials

Business cards

Brochures

Gift certificates/cards

Pricing sheets

Welcome materials

Referral cards

Intake forms

Consent forms

TAB Wellness Plans

Progress reviews

Program guides

Educational handouts

## Administrative materials

Letterhead

Invoices

Contracts

Waivers

Vendor forms

W-9/business documentation as applicable

Insurance documentation

Professional licenses/registrations as applicable

## Digital templates

PDF templates

Slide decks

QR codes

Downloadable guides

Forms

Email templates

Client portal assets

Appointment confirmation templates

# 19.11 — Existing-Client Communication Plan

| Communication | Timing | Purpose | Core subject/message |
| --- | --- | --- | --- |
| 1 — Heads-up | 2–3 weeks before launch | Prepare clients before they encounter the change. | TAB is evolving |
| 2 — Launch | Launch day | Introduce the new identity, four pillars and philosophy. | Welcome to TAB Wellness Collective |
| 3 — Experience | 2–4 weeks after launch | Shift the story from “new name” to “what the new TAB experience means for you.” | What TAB Wellness Collective means for you |

## Communication 1 — Heads-up

What is changing: name, visual identity, website and expanded expression of services.

Why the change is happening.

What is not changing: existing appointments, relationships and client history.

Whether the client needs to take any action — ideally no.

## Communication 2 — Launch

Introduce TAB Wellness Collective

Explain Transform. Align. Become.

Show the four service pillars

Link to the new site

Reinforce continuity and the Start Where You Are philosophy

## Communication 3 — Experience

Explain the TAB Method

Highlight Start Where You Are

Introduce resources and My TAB roadmap if ready

Show how services can connect without forcing cross-sell

# 19.12 — Referral & Professional Partners

Referral partners should be notified directly rather than left to infer the change from a website or social post.

Physicians

Physical therapists

Chiropractors

Doulas

Therapists

Other wellness providers

Gyms/trainers

Community organizations

Local businesses

Other referral sources

TAB Massage & Fitness is becoming TAB Wellness Collective. The new identity reflects our expanded whole-person model while preserving the same client-centered approach and relationships you’ve known.

Provide the new logo, website, service overview, contact information and updated referral instructions.

# 19.13 — Internal Team Readiness

| Common question | Approved answer |
| --- | --- |
| Why did TAB change its name? | Because the business has grown beyond “Massage & Fitness,” and the new identity better reflects TAB’s whole-person approach. |
| What does TAB mean? | Transform. Align. Become. |
| Is it a new company? | No. It is an evolution of TAB. |
| Can I still just book massage? | Absolutely. |
| Do I have to use all four services? | No. Start with what fits your needs. Services connect only when doing so genuinely supports your goals. |

# 19.14 — My TAB Transition

My TAB does not have to launch on the same day as the public rebrand. Do not delay the whole brand transition solely because the client portal is still in development.

If My TAB is ready: integrate it into the launch as the authenticated client experience.

If My TAB is not ready: continue using a straightforward “Client Login” path into Timely.

Only publish “My TAB — coming soon” if there is a credible delivery roadmap and the message will not linger indefinitely.

Introduce My TAB later as a meaningful product/experience release rather than an empty placeholder.

# 19.15 — Cutover Runbook

## 72 hours before launch

Freeze nonessential website changes

Complete a full site backup

Export critical Timely/client configuration where appropriate

Verify DNS and domain access

Verify Google/Search Console access

Confirm Stripe admin access

Confirm social logins

Run final link crawl

Run final redirect test

Complete staff briefing

Queue client announcement

## Launch sequence

Publish new website

Enable permanent redirects

Confirm SSL/certificates

Verify booking links

Update Timely

Update Stripe/customer branding

Update email signatures

Update Google Business Profile

Update social profiles

Publish launch announcement

Submit sitemap/Search Console move

Run end-to-end client-path tests

## Critical smoke tests

Google → website

Homepage → service page

Service page → booking

Start Where You Are form

Contact form

Timely booking

Timely Client Login

Stripe checkout/payment link

Email confirmation

Legacy URL → correct new URL

Social → website

QR codes

# 19.16 — First 30 Days

Monitor daily at first, then weekly. The initial question is not only “Is the new brand working?” but also “Did the rebrand create confusion?”

404 errors and redirect failures

Organic/search traffic

Search Console coverage

Google Business Profile visibility

Form submissions

Appointment conversion

Timely link behavior

Old email usage

Stripe/support questions

Client questions or “Are you the same company?” inquiries

Key launch metric Track the volume and source of rebrand-related confusion. Each repeated question is evidence of a touchpoint that may need clearer transition messaging.

# 19.17 — Days 30–90

Reduce “formerly TAB Massage & Fitness” where it is no longer adding value.

Continue external-link and directory updates.

Continue referral-partner outreach.

Monitor service-page and booking performance.

Collect client feedback on the new positioning and digital experience.

# 19.18 — Days 90–180

By this point, TAB Wellness Collective should stand on its own. Keep tabmassage.com, legacy URL redirects, legacy email aliases, the Our Story history and historical legal/accounting records permanently or for as long as they remain useful.

# 19.19 — Rebrand Master Inventory

Create a master tracker that becomes the control center for the launch. Every meaningful touchpoint should have an owner, target state and verification status.

| Touchpoint | Current state | New state | Owner | Ready? | Cutover | Verified? |
| --- | --- | --- | --- | --- | --- | --- |
| Website | TAB Massage & Fitness | TAB Wellness Collective | Web |  |  |  |
| Primary domain | tabmassage.com | New canonical domain | Web/IT |  |  |  |
| Google Business Profile | Legacy name | New name/brand | Owner/Marketing |  |  |  |
| Timely | Legacy brand | New name, links and templates | Operations |  |  |  |
| Stripe | Legacy public branding | New public branding | Finance |  |  |  |
| Email | Legacy domain | New domain + legacy aliases | IT |  |  |  |
| Instagram/Facebook/etc. | Legacy name/art | New name/art/links | Marketing |  |  |  |
| Exterior signage | Legacy | New identity | Owner/Vendor |  |  |  |
| Forms and PDFs | Legacy templates | New branded templates | Operations |  |  |  |

# 19.20 — Rebrand Governance Rules

| Rule | Standard |
| --- | --- |
| 1. One canonical name | Use TAB Wellness Collective. Do not create interchangeable public variations. |
| 2. One migration story | TAB has evolved — not disappeared. |
| 3. One source of truth | Use the master transition inventory to control every touchpoint. |
| 4. Preserve legacy equity | Redirect and forward rather than delete or recreate unnecessarily. |
| 5. Client continuity comes first | No branding change should make a current client wonder whether their appointment, practitioner, account, payment relationship or access still exists. |

# 19.21 — Recommended Ownership Model

Even in a small business, assigning explicit ownership prevents launch-day gaps. One person can hold multiple roles, but every domain should have a named accountable owner.

| Workstream | Accountable role |
| --- | --- |
| Brand / final approvals | Business owner / brand lead |
| Website, domain, redirects, analytics | Web/technical owner |
| Timely configuration | Operations / scheduling owner |
| Stripe and financial touchpoints | Finance / owner |
| Google and local directories | Marketing / owner |
| Email/domain aliases | Technical owner |
| Social / launch content | Marketing / social owner |
| Physical signage / print | Owner / vendor coordinator |
| Client communications | Owner / client experience lead |
| Partner communications | Owner / referral relationship lead |

# 19.22 — Recommended Timeline at a Glance

| Window | Major activities |
| --- | --- |
| T-8 to T-6 weeks | Clearance, domains, system inventory, website build, redirect mapping, signage order. |
| T-6 to T-4 weeks | Timely/Stripe staging, email setup, collateral, social assets, forms, QA. |
| T-3 to T-2 weeks | Client heads-up, partner heads-up, staff training, final site/content QA. |
| T-1 week | Freeze key assets, final smoke tests, queue launch communications, verify all credentials. |
| Launch | Coordinated digital/physical cutover and end-to-end testing. |
| +1 to +30 days | Intensive monitoring, confusion reduction, broken-link/SEO cleanup. |
| +30 to +90 days | Reduce transitional language, expand partner/directory cleanup. |
| +90 to +180 days | Steady-state brand; legacy references become primarily historical/technical. |

# 19.23 — Step 19 Closeout

Step 19 completes the practical migration plan from TAB Massage & Fitness to TAB Wellness Collective. The plan deliberately prioritizes continuity: existing clients should not lose access, history, trust, bookings, payment context or familiarity merely because the brand has evolved.

Step 19 success criterion A new visitor understands TAB Wellness Collective immediately, while an existing TAB Massage & Fitness client experiences the change as familiar, intentional and seamless.

## Permanent legacy assets to retain

tabmassage.com and its redirect map

Legacy email aliases

Historical About / Our Story references

Historical legal/accounting records

Relevant legacy content that supports search or client history

## Next recommended deliverable

With Steps 1–19 complete, the next logical deliverable is a consolidated TAB Brand & Experience Playbook that becomes the authoritative source for brand foundation, services, customer journey, messaging, website/digital architecture, naming rules, visual identity and rollout standards.

# Appendix A — Master Launch Checklist

| Workstream | Checklist item | Status |
| --- | --- | --- |
| Legal & ownership | Trademark clearance complete | ☐ |
| Legal & ownership | Michigan filing/name action complete | ☐ |
| Legal & ownership | Primary domain secured | ☐ |
| Legal & ownership | Social handles reserved | ☐ |
| Website | New site production-ready | ☐ |
| Website | Redirect map tested | ☐ |
| Website | Analytics configured | ☐ |
| Website | Search Console verified | ☐ |
| Website | Sitemap submitted | ☐ |
| Website | Old domain retained | ☐ |
| Timely | Business name/logo updated | ☐ |
| Timely | Booking links verified | ☐ |
| Timely | Service descriptions reviewed | ☐ |
| Timely | Emails/reminders reviewed | ☐ |
| Timely | Forms reviewed | ☐ |
| Stripe | Public branding updated | ☐ |
| Stripe | Support contact updated | ☐ |
| Stripe | Receipt/invoice branding reviewed | ☐ |
| Stripe | Statement descriptor documented | ☐ |
| Email | New-domain addresses live | ☐ |
| Email | Old addresses forwarding | ☐ |
| Email | Signatures updated | ☐ |
| Google/local | Google Business Profile updated | ☐ |
| Google/local | Local directories prioritized | ☐ |
| Google/local | NAP master record confirmed | ☐ |
| Social | Display names/handles updated | ☐ |
| Social | Avatar/banner updated | ☐ |
| Social | Pinned launch post live | ☐ |
| Social | Website/booking links updated | ☐ |
| Physical | Exterior signage installed | ☐ |
| Physical | Interior branding updated | ☐ |
| Physical | Temporary transition messaging visible where needed | ☐ |
| Operations | Forms/PDFs updated | ☐ |
| Operations | Staff scripts complete | ☐ |
| Operations | Client announcements sent | ☐ |
| Operations | Partner announcements sent | ☐ |
| QA | Desktop/mobile smoke tests passed | ☐ |
| QA | Old URL tests passed | ☐ |
| QA | Booking flow passed | ☐ |
| QA | Payment flow passed | ☐ |
| QA | Email confirmation flow passed | ☐ |

# Appendix B — Transition Messaging Templates

## Short client transition statement

TAB Massage & Fitness is becoming TAB Wellness Collective. Our new name better reflects the broader, whole-person approach TAB has grown into while preserving the same trusted relationships and personalized support you already know.

## Short partner transition statement

TAB Massage & Fitness is becoming TAB Wellness Collective. The new identity reflects our expanded whole-person model while preserving the same client-centered approach and relationships you’ve known.

## Temporary website announcement bar

TAB Massage & Fitness is now TAB Wellness Collective. Same commitment. A broader expression of what TAB has become.

## Temporary social bio

TAB Wellness Collective • formerly TAB Massage & Fitness • Massage • Strength • Women’s Wellness • Life Coaching • Transform. Align. Become.

## Temporary email signature note

TAB Wellness Collective — formerly TAB Massage & Fitness | Transform. Align. Become.

# Appendix C — Platform & Migration Notes

The implementation recommendations in this playbook were informed by current platform guidance reviewed during Step 19. Because vendor interfaces and requirements can change, revalidate the exact configuration steps immediately before cutover.

| Area | Guidance to revalidate before launch |
| --- | --- |
| Google Search / domain move | Permanent redirects, canonical URLs, sitemap, Search Console verification/change-of-address workflow, monitoring of indexing. |
| Google Business Profile | Business-name rules, reverification behavior, profile field requirements and categories. |
| Timely | Business-details update flow, location naming, booking-link behavior, email/invoice branding and reminder behavior. |
| Stripe | Branding, support information, Customer Portal/receipt behavior, statement-descriptor requirements and metadata practices. |

Primary sources referenced in the working analysis included Google Search Central, Google Business Profile Help, Timely Help Centre and Stripe documentation. Final launch owners should use the latest vendor documentation rather than relying solely on this static playbook.